## Q1-2021
Week | ML Microservice API | Estimate (Hours)
2021-01-01 | Project Repository Setup & Configuration | 2
2021-01-08 | Azure Cloud Shell Configuration | 1
2021-01-15 | Github Actions Configuration | 3
2021-01-22 | Azure App Service Configuration | 2
2021-01-29 | Setup & Configure Azure Pipelines | 3
2021-02-05 | Project End to End Testing | 5
2021-02-12 | Project Load / Stress Testing | 7
2021-02-19 | Project Documentation | 7
2021-02-26 | Quality Assurance Testing | 7
2021-03-05 | End User Testing | 11
2021-03-12 | Project Review | 2
2021-03-19 | Go Live | 2
2021-03-26 | Production Support | 10
Goals
Project hosted on a Github Repository
Continuous Integration with Github Actions
App deployed to Azure App Service
Continuous Delivery with Azure Pipelines

## Y-2021
Month | ML Microservice API | Estimate (Days)
2021-01-01 | Project Setup with Continuous Integration & Delivery | 15
2021-02-01 | Project QA / E2E Testing & Documentation | 13
2021-03-01 | Project Review & Go Live | 11
2021-04-01 | Automated Tests | 17
2021-05-01 | Implement Security: Authentication and Authorization | 15
2021-06-01 | Tracing & Logging | 12
2021-07-01 | Nationwide Support: Support Multiple States | 10
2021-08-01 | Alerts & Application Monitoring | 14
2021-09-01 | Realtime Data Fetch | 15
2021-10-01 | Asynchronous Data Processing | 13
2021-11-01 | Backend APIs | 15
2021-12-01 | Front End Web App | 15
Goals
Project code hosted on Github with Continuous Integration
App deployed to Azure App Service with Continuous Delivery
Documentation of the project
Non Functional Features: Security, Logging & Monitoring
Multi State support with Realtime Data Fetch
A Responsive Frontend Web App for End Users